## Open Actions Register
OPEN ACTIONS REGISTER — Rani Enterprises (Robotic Sealant Dispenser Machine)
Action ID | Description of Gap / Safety Action | Category | Priority | Responsibility | Target Date | Status
OA-P7-001 | Formally execute Machine Safety Risk Assessment (RA) and attach report | Risk Assessment | High | Rani Enterprises / Customer | Prior to Commissioning | Open
OA-P7-002 | Provide complete As-Built Electrical Schematics and Single Line Diagram (SLD) | Documentation | High | Rani Enterprises Electrical Engineering | Prior to Final Handover | Open
OA-P7-003 | Provide Pneumatic Piping & Instrumentation Diagram (P&ID) / SMC FRL layout | Documentation | Medium | Rani Enterprises Mechanical Engineering | Prior to Final Handover | Open
OA-P7-004 | Verify incoming mains supply voltage, current rating (Amps), and nameplate specs | Technical Spec | Medium | Customer Site Electrical Team | During Site Installation | Open
OA-P7-005 | Validate complete Mitsubishi HMI IPC Alarm & Fault Code Register | Control System | Low | Automation Supplier | During Dry-run Testing | Open