## Open Actions
ID | Description | Category | Priority | Responsibility | Target Date | Status
OA-P2G-001 | Confirm full E-Stop inventory. Photo shows ES-01 on control column below HMI; verify whether additional E-Stops exist on left/right stations, rear, or pendant. | Safety Device | High | Manufacturer / End User | TBD | Open
OA-P2G-002 | Obtain electrical schematic drawings for inclusion in Section 8 (not available in assessment package used for this sample). | Documentation | High | Manufacturer | TBD | Open
OA-P2G-003 | Obtain pneumatic schematic drawings for inclusion in Section 9. | Documentation | Medium | Manufacturer | TBD | Open
OA-P2G-004 | Confirm HMI/PLC model, alarm code list, and backup documentation for Section 10. | Documentation | Medium | Manufacturer | TBD | Open
OA-P2G-005 | Confirm machine nameplate data: model number, serial number, asset number, manufacturing date as marked on machine. | Documentation | High | Manufacturer / End User | TBD | Open
OA-P2G-006 | Confirm pneumatic isolation device type (lockable ball valve vs other) and presence of lockout hasp as-built. | LOTO | High | Manufacturer / End User | TBD | Open
OA-P2G-007 | Safety-rated controller (SRPCS) model and configuration to be documented from OEM data. | Safety Device | Medium | Manufacturer | TBD | Open
OA-P2G-008 | Light curtain distance to hazard zone (mm) incomplete in assessment — verify and record for safety distance validation. | Safety Device | High | Independent Safety Consultant / Manufacturer | TBD | Open

## Meta
Project | P2-Grok-Sample
Machine | Tilting Machine
Status | Grok Sample / Draft
Revision | V1.1
Note | Standalone Open Actions Register — not embedded in OSM