## Open Actions
ID | Description | Category | Priority | Responsibility | Target Date | Status
OA-P7-001 | Commission a formal Machine Safety Assessment by an Independent Safety Consultant. No RA report exists; residual risk and PLr claims cannot be finalised from photos alone. | Risk Assessment | High | OEM / End User | TBD | Open
OA-P7-002 | Confirm electrical supply data: voltage, phases, frequency, full-load current / kW, machine serial number, year of manufacture. Photograph complete nameplate if present. | Documentation | High | OEM / End User | TBD | Open
OA-P7-003 | Provide electrical schematic drawings for Section 9 insert (customer may paste drawings). Include panel layout and main isolator circuit. | Documentation | High | OEM | TBD | Open
OA-P7-004 | Provide pneumatic schematic drawings for Section 9 insert (door cylinders, FRL, dispenser air path, isolation valves). | Documentation | High | OEM | TBD | Open
OA-P7-005 | Validate front automatic safety door: closing force/edge protection, interlock behaviour, and residual risk of no light curtain at operator load face. Document required administrative controls. | Safety Device | High | Independent Safety Consultant / OEM | TBD | Open
OA-P7-006 | Document sealant product identity, SDS, dispenser capacity, pot life / tip dry-out limit, and confirm idle parking time policy (HMI shows 3.0 min). | Process / Chemical | High | OEM / End User | TBD | Open
OA-P7-007 | Confirm pneumatic isolation device is lockable (ball valve/hasp) and isolator lockout hardware (hasp/padlock) is available for LP-01/LP-02. | LOTO | High | OEM / End User | TBD | Open
OA-P7-008 | Export full HMI/PLC alarm list and I/O map from project file (only partial live alarms captured in photos). | Documentation | Medium | OEM | TBD | Open
OA-P7-009 | Confirm exact Mitsubishi PLC and HMI model numbers, software version, and network addresses for maintenance records. | Documentation | Medium | OEM | TBD | Open
OA-P7-010 | Fill end-user facility name, site address, PPE matrix, training matrix, and authorised persons list. | Documentation | Medium | End User | TBD | Open
OA-P7-011 | Confirm robot axis speed limits, program ownership (who may teach), and whether teach mode is locked for production operators. | Operation | Medium | OEM / End User | TBD | Open
OA-P7-012 | Map tower-light colour meanings (red/amber/green) to machine states for operator training. | Operation | Low | OEM | TBD | Open

## Meta
Project | P7-Rani-Sealant
Machine | Robotic Sealant Dispenser Machine
Manufacturer | Rani Enterprises
Status | Draft
Revision | V1.0
Note | Standalone Open Actions Register — not embedded in OSM