## Full Register
ID | Description | Category | Priority | Responsibility | Target Date | Status | Notes
OA-P8-001 | Manufacturer name, model number, serial number not available. Retrofit unit, no nameplate. | Documentation | High | Customer | TBD | Open | Confirm or source manufacturer records
OA-P8-002 | Exact physical location of pneumatic shut-off/exhaust valve not specified in source data | Documentation | Medium | Customer | TBD | Open | Needed for LOTO point diagram accuracy
OA-P8-003 | Fixed guard G001 uses a removable retaining lever — identified as a residual risk in source assessment | Safety Gap | High | Customer/Engineer | TBD | Open | Consider tamper-resistant redesign
OA-P8-004 | Acrylic guard dimensions for live bus bar area (G004-Busbar acc) not finalised — source lists "xxx mm" placeholders | Schematic | Medium | Customer | TBD | Open | Confirm dimensions and installation
OA-P8-005 | IP2X protection for control panel live terminals not confirmed present | Safety Gap | High | Customer | TBD | Open | Per source assessment R005
OA-P8-006 | Over-voltage/power fluctuation protection device not confirmed installed | Safety Gap | Medium | Customer | TBD | Open | Per source assessment R006
OA-P8-007 | Specific PPE item list (hearing protection class, glove type, etc.) not itemised in source data | Documentation | Low | Customer | TBD | Open | General PPE only specified
OA-P8-008 | Detailed OEM-recommended maintenance intervals not available | Maintenance | Medium | Customer | TBD | Open | Only activities described in source RA used
OA-P8-009 | No electrical, pneumatic, or hydraulic schematics available | Schematic | Medium | Customer | TBD | Open | Tier C — sections 8–10 omitted from manual
OA-P8-010 | No HMI alarm/fault code list available (MORPHEE software referenced but not documented) | Software | Low | Customer | TBD | Open | Section 11 omitted — Tier C
OA-P8-011 | No site photographs provided; manual contains placeholder image references only | Documentation | Medium | Customer | TBD | Open | Photos exist per customer but not uploaded to this project
OA-P8-012 | Site photographs are described/embedded in the source Machine Safety Assessment Report but were not separately uploaded for this manual | Documentation | Low | Customer | TBD | Open | Extract from RA report if usable, else request fresh site photos

## Summary by Category
Category | Count | IDs | Notes
Documentation | 5 | OA-P8-001, OA-P8-002, OA-P8-007, OA-P8-011, OA-P8-012 | Missing manufacturer data, locations, PPE list, photos
Safety Gap | 3 | OA-P8-003, OA-P8-005, OA-P8-006 | Guard lever, IP2X, over-voltage protection
Schematic | 2 | OA-P8-004, OA-P8-009 | Acrylic guard dims; no electrical/pneumatic/hydraulic schematics
Maintenance | 1 | OA-P8-008 | OEM intervals unavailable
Software | 1 | OA-P8-010 | No HMI alarm/fault codes (MORPHEE)
TOTAL | 12

## Revision History
Revision | Date | Description | Author
V1.0 | [PLACEHOLDER — issue date] | Initial Open Actions Register for P8 Low Energy Test Bench OSM | Certified Safety Professional