## Open Actions Register
OPEN ACTIONS REGISTER — BG Snap Assembly Machine (P4)
IndoMIM Technologies Pvt. Ltd. ¦ End User: Tata Electronics, Hosur ¦ Document: IndoMIM-BGSnap-OAR-001 ¦ Rev: V1.0 ¦ April 2026 ¦ Prepared by: Ravikumar, Certified Safety Professional
OA ID | Section Ref | Category | Description of Open Action | Risk Level | Recommended Action | Responsibility | Target Date | Status | Closure Evidence / Notes
OA-P4-001 | Sec. 4.2 | Safety - LOTO | All five LOTO isolation points (LP-01 to LP-05) identified from DFM V1.4 and Machine Safety Assessment Report. Physical location, labelling, and hasp availability for each point must be verified during site visit at Tata Electronics, Hosur before LOTO section is finalized. | H | Site visit to Tata Electronics, Hosur. Physically verify LP-01 to LP-05 locations, confirm lockout hasp availability, photograph each point. Tata Electronics maintenance team to sign off. | Ravikumar (site visit) | Dry run | OPEN
OA-P4-002 | Sec. 8.2 | Documentation - Electrical | Electrical schematic drawings for the BG Snap Assembly Machine have not been provided at time of manual preparation. Full drawing set required: single-line diagram, control circuit, E-stop dual-channel circuit, servo/STO wiring, KUKA interface, Maglev PLC wiring, cable schedule. | H | Indo-MIM electrical design team to supply complete drawing set in A3 format at 300 DPI minimum. Insert into Section 8 before manual finalization. | Indo-MIM Engineering | Before finalization | OPEN
OA-P4-003 | Sec. 11.3 / 2.9 | Software - HMI | Complete HMI alarm code list has not been provided at time of manual preparation. Section 11 contains placeholder content only. Alarm list must include: code, description, station, priority level, probable cause, operator action, reset procedure. | M | Indo-MIM software engineering team to extract complete alarm list from C# application alarm module and SQL alarm table. Supply in structured table format for insertion into Section 11. | Indo-MIM Engineering | Before finalization | OPEN
OA-P4-004 | Sec. 2.1 | Documentation - Machine ID | Machine weight data not available at time of manual preparation. Total line weight and individual station weights required for machine identification table and safe handling documentation. | L | Indo-MIM to confirm total line weight and individual station weights from structural design data or weighing at factory. Insert into Section 2.1 machine identification table. | Indo-MIM Engineering | Before finalization | OPEN
OA-P4-006 | Sec. 4.7 | Safety - LOTO | Partial isolation procedure conditions and authorization protocol for troubleshooting scenarios (energizing specific stations while others remain isolated) requires finalization by Indo-MIM maintenance supervisor and Tata Electronics safety representative before manual is released. | H | Indo-MIM maintenance supervisor and Tata Electronics EHS representative to review Section 4.7 draft framework, agree authorization protocol, and sign off. Update Section 4.7 in V2.0. | Indo-MIM + Tata Electronics | Before V2.0 | OPEN
OA-P4-007 | Sec. 5.2 | Safety - E-Stop | Physical E-stop locations, exact mounting heights, and panel positions must be verified during site visit at Tata Electronics, Hosur. Locations listed in Section 5.2 are derived from DFM V1.4 HMI layout only. | H | Site visit to Tata Electronics, Hosur. Physically verify ES-01 to ES-06 locations, mounting heights, and panel positions. Photograph each E-stop device. Update Section 5.2 and Figure 5-1. | Ravikumar (site visit) | Dry run | OPEN
OA-P4-008 | Sec. 7.8 | Maintenance - Lubrication | Lubrication schedule pending confirmation with Indo-MIM engineering: lubricant types, approved brands, application quantities, and confirmed service intervals for HIWIN axes, Toyo axes, KUKA robot joints, SMC pneumatic cylinders, and rotating cylinder pivot points. | M | Indo-MIM engineering team to confirm lubrication specifications for all components. Supply structured table (Component ¦ Lubricant Type ¦ Brand ¦ Application Point ¦ Interval ¦ Quantity). Insert into Section 7.8 and create lubrication point diagram. | Indo-MIM Engineering | Before finalization | OPEN
OA-P4-009 | Sec. 7.10 | Maintenance - Troubleshooting | Troubleshooting guide for common fault conditions, probable causes, and corrective actions is pending input from Indo-MIM engineering team and Tata Electronics maintenance team following site visit and dry run. | M | Conduct operator and maintenance interviews at dry run. Indo-MIM to supply fault conditions and corrective actions from machine commissioning data. Populate troubleshooting table in Section 7.10. | Indo-MIM Engineering + Tata Electronics Maintenance | Before finalization | OPEN
OA-P4-010 | Sec. 9.2 | Documentation - Pneumatic | Pneumatic schematic drawings have not been provided at time of manual preparation. Full circuit diagram required: main air supply, FRL unit, solenoid valve banks, individual actuator circuits (all stations), symbol legend per ISO 1219-1, pressure settings table. | H | Indo-MIM pneumatic design team to supply complete circuit diagram in A3 format at 300 DPI minimum. Insert into Section 9 before manual finalization. | Indo-MIM Engineering | Before finalization | OPEN
OA-P4-011 | Sec. 12.5 | Safety - Guarding | Location and operation of emergency mechanical door release on each of the six interlocked station doors must be confirmed and photographed during dry run at Tata Electronics, Hosur. Training on emergency release must be included in maintenance technician induction. | H | Site visit: locate and photograph emergency release on all six station doors. Document release operation in Section 12.5. Include emergency release training in maintenance induction checklist. | Ravikumar (site visit) | Dry run | OPEN
OA-P4-012 | Sec. 12.6 | Safety - Light Curtain | Confirmation of whether light curtain muting is implemented at S1 and S6 is pending site visit verification. If muting is confirmed, muting sensor locations and muting window parameters must be documented and added to Section 12.6 before manual is finalized. | M | Site visit: confirm whether muting is implemented at S1 and S6 light curtains. If yes, document muting sensor locations, muting window parameters, and muting logic in Section 12.6. | Indo-MIM Engineering + site visit | Dry run | OPEN
OA-P4-013 | Sec. 12.4 | Safety - Device Inventory | Safety device inventory (SD-01 to SD-17) derived from DFM V1.4 and Machine Safety Assessment Report. Physical installation, cable routing, device mounting positions, and label verification must be confirmed during dry run at Tata Electronics, Hosur. | H | Site visit: physically verify all 17 safety devices against inventory table. Confirm device IDs, mounting positions, cable routing, and safety label presence. Update Section 12.4 table post dry run before V2.0. | Ravikumar (site visit) | Dry run | OPEN
OA-P4-014 | Sec. 4.6 | Safety - LOTO | LOTO Energy Isolation Diagram (Figure 4-1) has not been created. Full machine top-view layout showing LP-01 to LP-05 locations, colour-coded by energy type, with LP-ID labels and lockout hasp symbols is required as A3 shop-floor poster. | H | Create LOTO Energy Isolation Diagram from DFM V1.4 layout and site visit photographs following OA-P4-001 closure. Print as A3 poster and affix at machine. Insert high-resolution version into Section 4.6. | Ravikumar (post site visit) | Before finalization | OPEN
OA-P4-015 | App. A - RR-13 | Safety - Ergonomic | Tray weight for HSG-loaded input trays has not been confirmed. RR-13 ergonomic risk assessment and tray handling guidance in Appendix A are based on unconfirmed tray weight. Confirmed weight required to finalize manual handling risk rating. | M | Indo-MIM to confirm loaded tray weight. If tray weight exceeds 10 kg, review manual handling risk rating and update tray loading procedure in Section 6.7 to specify two-person lift requirement. Update RR-13 in Appendix A. | Indo-MIM Engineering | Before finalization | OPEN
LEGEND & NOTES
Status values | OPEN - action not yet started ¦ IN PROGRESS - action underway ¦ CLOSED - verified and signed off
Risk Level | H = High (immediate action required) ¦ M = Medium (action within 30 days) ¦ L = Low (monitor)
Category | Safety - LOTO ¦ Safety - E-Stop ¦ Safety - Guarding ¦ Safety - Light Curtain ¦ Safety - Device Inventory ¦ Safety - Ergonomic ¦ Documentation - Electrical ¦ Documentation - Pneumatic ¦ Documentation - Machine ID ¦ Software - HMI ¦ Maintenance - Lubrication ¦ Maintenance - Troubleshooting
Total OAs | 14 Open Actions documented in V1.0. All must be closed before manual V2.0 is released and machine placed into production service.
Prepared by: | Ravikumar, Certified Safety Professional |  |  |  |  | Date:
Reviewed by (Indo-MIM): | [5 empty] | Date:
Approved by (Tata Electronics EHS): | [5 empty] | Date:

## Summary by Category
OPEN ACTIONS — SUMMARY BY CATEGORY
Category | Count | Risk Level(s)
Documentation - Electrical | 1 | H
Documentation - Machine ID | 1 | L
Documentation - Pneumatic | 1 | H
Maintenance - Lubrication | 1 | M
Maintenance - Troubleshooting | 1 | M
Safety - Device Inventory | 1 | H
Safety - E-Stop | 1 | H
Safety - Ergonomic | 1 | M
Safety - Guarding | 1 | H
Safety - LOTO | 3 | H
Safety - Light Curtain | 1 | M
Software - HMI | 1 | M
TOTAL | 14 | 8 High / 5 Medium / 1 Low

## Revision History
REVISION HISTORY
Rev | Date | Author | Description of Changes
V1.0 | April 2026 | Ravikumar | Initial issue — 14 Open Actions documented from manual V1.0.